## Story Card
Story Number | User Story | Tasks | Task Breakdown | Task Breakdown
1 | As a user I want to stay standing so that I do not hurt myself | Find data for gait Analyze data Develop model | Database structure Find stats on data Validation test for data Developing architecture | Data storage (internal &/ cloud) Create algorithm
2 | As a user I want to know when I am at risk of falling so that I I will know when I fall | Define abnormal gait Define normal gait Get sensor data | Data type (accleration to person) Data value type (numeric/float) Separate dimentions Access accelerometer
3 | As a user I want the device to work better the more I use it so that I won't worry my family | Create notification Able to notify specific people If fall, have time delay for automatic notification/call | Conditional: Message Sound Call
4 | As a user I want my family to know if I have fallen so that I will get the help I need | Notify other family members Call family Create automated calling Facebook message
5 | As a user I want others around me to receive infromation that I have fallen so that I can receive help | Message people 10m or closer distance Give location for fall victim if 100m Drones
6 | I want to see shoe data for the gait pattern as a part of the algorithm | Get shoe data Connect app via bluetooth | Collect data via bluetooth
7 | Able to add GPS data and other location data | Automatic drop pin location
8 | Have a good presentation

## Priority List
Priority | Tasks | Effort /Cost (1-100) | Risk (1-100) | Initiating Task | Expected Results | Acceptance test | Risk Accessment/Importance
1 | Creating SQLite database for data input | 75 | 100
2 | Set up name within a database | 60 | 80
3 | Set up numbers within a database | 30 | 60
4 | Create UI for inputting data and input list | 20 | 50
5 | Test reponsive UI | 50 | 90
6 | Send message notification | 20 | 50 | Press send message/ after 10 second delay | A SMS message is received by correct party | The correct message is received | Important to notify concerned parties
7 | Save message data in database | 40 | 70
8 | Reduce computations of algorithm | 50 | 100
9 | Median changing within an interval
10 | Impliment Algorithm in Java/Android | 90 | 100
Icebox
6 | Validation test for data | 100 | 90
7 | Find data storage method | 50 | 50
8 | Access acellerometer on phone | 25 | 100
9 | Define data type | 1 | 100
10 | Define data value type | 1 | 50
12 | Message notification | 20 | 1
13 | Sound notification | 20 | 1
14 | Call notification | 20 | 1
15 | Message | 20 | 1
6 | Create Algorithm | 50 | 85
7 | Impliment Algorithm | 90 | 100
8 | Test Algorithm | 80 | 100
100 | Filter IIR (impluse response) | 100 | 100
100 | Embed HTML5 with Android | 100 | 100

## Task Risk Assessment
Tasks | Risk (1-100) | Risk Description | Acceptance Test
Find data for gait | 100 |  | Similar pattern of gait
Analyze data | 10
Database structure | 90
Develop Architecture | 100
Separate dimensions | 50
Validation test for data | 90
Find data storage method | 50
Access acellerometer on phone | 100
Define data type | 100
Define data value type | 50
Create conditions for notification | 100
Message notification | 1
Sound notification | 1
Call notification | 1
Message | 1
Create Algorithm | 85
Impliment Algorithm | 100
Test Algorithm | 100

## Tasks Completed
Tasks | Effort /Cost (1-100) | Risk (1-100) | Initiating Task | Expected Results | Acceptance Tests
Find data for gait | 5 | 100 | Ask Jahangir for data | Receive data | Make sure data is of gait analysis
Analyze data | 50 | 10 | Plot data | Find patterns within the data | Analyze data with known data
Develop Architecture | 60 | 100 | Create a static equation | Working software with tools | Pass or Fail test
Separate dimensions | 10 | 50 | Obtain accelerometer data | Given data in x,y,z | Phone orientation movement
Velocity | 125
Create conditions for notification | 40 | 100 | A fall is detected | Will open the notification | Viewable notification screen | Need notification for overall app
Collect more data | 25 | 25 | Speak to volunteers for obtain gait data | Get some amount of data (x,y,z) | Data within a table for the subject | More data will provide a better analysis
Run descriptive statistics on the data | 10 | 20 | Find functions in R to run the stats | Mean, standard deviation, median | Determine if the data is reasonable for the test set | The stats must be reasonable otherwise an algorithm will be based on unreasonable data
Build analysis of current data | 50 | 80 | Compile all recorded data | Have a pattern to notify whether ranges are in or out of range | Determine if the data is reasonable for the test set | Proper analysis is needed for being the algorithm
Apply real time accelerometer data | 10 | 25 | Place the application to read accelerometer data | Accelerometer output values will change while the phone is moving | Accelerometer output values will change according to the phone's orientation | Applying the apporiate sensors from literature
Load phone with accelerometer data app | 5 | 25 | Create installer for phone | Open application in phone | Show application template on the phone | The application needs to be on the phone
Create android activity connections | 25 | 100 | Run application | Pressing a button will connect to another activity | Pressing a button will connect to another activity | In order to change notification and functionalility between different sections of the app, activities must be connect to one another
Connect notification with conditions app | 10 | 100 | Make sure both sets of code can be run together | If conditions are met, the notification app will come up | All buttons work and interact with all components of the app | Functionality of the app is dependent on multiple connections between activities
Velocity | 175